## Sheet1
DOUGLAS |  |  |  | DOUGLAS
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES NEEDED
NON-CO | NOW |  | INVENTORY EQUIPMENT AND SUPPLIES | NEED INVENTORY SYSTEM TO WORK AT BOOTH
NON-CO | NOW |  | BOX UP ALL NON-ESSENTIAL SUPPLIES AND EQUIPMENT TO TAKE TO BOOTH PUT ON PALLET. | PALLETS, PATRICK HAS SEMI FULL OF PALLETS, NEED PICKEDUP
NON-CO | NOW |  | NON
NON-CO | NOW |  | DECIDE ON WHICH FURNITURE WILL GO AND WHAT WILL NOT. DISPOSE OF /SELL
NON-CO | NOW |  | CABINET IN LOUNGE - PUT TOP ON USE IN CLASSROOM #3 @ BOOTH
NON-CO | NOW |  | INVENTORY AND PACK UP JEWLERY ROOM, PUT ON JEWERLY PALLET
GENERAL |  |  |  | GENERAL
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
NON-CO | NOW |  | CONSOLIDATE AND ORGANIZE ALL DEMO MATERIALS. FIND TEMP HOME. ONLY KEEP WHAT CAN/WILL BE REUSED.D DISPOSE OF OR AUCTION REST. FIND BEST HOME IN TEXTILE WET ROOM, OR BOILER ROOM
CO | IN PROGRESS | PAULA | ALL ROOM SIGNAGE (INCLUDING ADA)
ENTRY WAY- EAST |  |  |  | ENTRY WAY- EAST
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
CO | NOW |  | DOOR OPENER MUST MEET 15 LB
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | NOW |  | FIX ANY ROTTED WOODWORK/TRIM
NON-CO | NOW |  | FIX BROKEN OR LOOSE TILE
NON-CO | NOW |  | REMOVE ALL TRASH OR MISC / FIND HOME OR DISPOSE
NON-CO | NOW |  | PREP FOR PAINT. REMOVE ALL NAILS, UN-NECESSARY HARDWARE, FILL HOLES AND CAULK AS NEEDED
ENTRYWAY- WEST |  |  |  | ENTRY WAY- WEST
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | NOW |  | FIX ANY ROTTED WOODWORK/TRIM
NON-CO | NOW |  | FIX BROKEN OR LOOSE TILE
NON-CO | NOW |  | REMOVE ALL TRASH OR MISC / FIND HOME OR DISPOSE
NON-CO | NOW |  | PREP FOR PAINT. REMOVE ALL NAILS, UN-NECESSARY HARDWARE, FILL HOLES AND CAULK AS NEEDED
ENTRYWAY- NORTH |  |  |  | ENTRY WAY- NORTH
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | NOW |  | FIX ANY ROTTED WOODWORK/TRIM
NON-CO | NOW |  | FIX BROKEN OR LOOSE TILE
NON-CO | NOW |  | REMOVE ALL TRASH OR MISC / FIND HOME OR DISPOSE
NON-CO | NOW |  | PREP FOR PAINT. REMOVE ALL NAILS, UN-NECESSARY HARDWARE, FILL HOLES AND CAULK AS NEEDED
ENTRY WAY- SOUTH |  |  |  | ENTRY WAY- SOUTH
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | NOW |  | FIX ANY ROTTED WOODWORK/TRIM
NON-CO | NOW |  | FIX BROKEN OR LOOSE TILE
NON-CO | NOW |  | REMOVE ALL TRASH OR MISC / FIND HOME OR DISPOSE
NON-CO | NOW |  | PREP FOR PAINT. REMOVE ALL NAILS, UN-NECESSARY HARDWARE, FILL HOLES AND CAULK AS NEEDED
HALLWAYS - EAST / WEST |  |  |  | HALLWAYS - EAST/WEST
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
NON-CO | NOW |  | PREP FOR PAINT, REMOVE ALL GLUE, TAPE UN-NECESSARY HARDWARE, IE CLASSROOM # PLATES, FILL HOLES, FIX CRACKS IN BRICK/CINDER BLOCKS
NON-CO | HOLD |  | COVER ALL OPEN ELEC BOXES
NON-CO | HOLD |  | BUILD OUT DISPLAY FOR OLD GATE HOLES
NON-CO | HOLD |  | DECIDE ON LOCATION OF DONOR WALL. IF NEAR EAST DOOR. REMOVE BULLETIN BOARD
NON-CO | NOW |  | RUN POWER FOR COMPUTER SCREEN
HALLWAY - NORTH/SOUTH |  |  |  | HALLWAY- NORTH/SOUTH
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
NON-CO | NOW |  | PREP FOR PAINT, REMOVE ALL GLUE, TAPE, UN-NECESSARY HARDWARE, IE CLASSROOM # PLATES, FILL HOLES, FIX CRACKS.
NON-CO | HOLD |  | COVER ALL OPEN ELEC BOXES
NON-CO | HOLD |  | DESIGN AND BUILD OUT DISPLAY FOR OLD GATE HOLES
FRONT OFFICE / CORRIDOR |  |  |  | FRONT OFFICE / CORRIDOR
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
CO | NOW |  | REMOVE DOORS AND DOOR FRAMES.
NON-CO | NOW |  | FINISH TRIM WORK OF DOOR OPENINGS
NON-CO | NOW |  | DO WE WANT THE HEATER REGISTER REMOVED?
NON-CO | NOW |  | FIX LOOSE TILES AND MISSING TILES AROUND DOOR OPENINGS
NON-CO | NOW |  | REMOVE UN-USED CONDUIT AND BOXES FROM SOUTH WALL.
NON-CO | NOW |  | REMOVE BULLETIN BOARDS FROM SOUTH WALL
NON-CO | NOW |  | CLEAN AND PREP WALLS FOR PAINT
NON-CO | HOLD |  | DESIGN AND BUILD NEW FRONT RECEPTION COUNTER WHERE GLASS WINDOWS ARE NOW
NON-CO | HOLD |  | REMOVE GLASS WINDOWS
FRONT NON-ADA RESTROOM |  |  |  | FRONT NON-ADA RESTROOM
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
NON-CO | NOW |  | THOROUGH CLEANING, FLOOR, TOILET, SINK AND CABINET
NON-CO | HOLD |  | REPLACE FAUCET | NEED FAUCET
NON-CO | NOW |  | FIND TRASH CAN
NON-CO | NOW |  | FIND HOME FOR TOILET PAPER DISPENSERS - GARAGE SHELF
NON-CO | NOW |  | FIND HOME FOR TOILET REPAIR PARTS - GARAGE SHELF
FRONT ADA RESTROOM |  |  |  | FRONT ADA RESTROOM
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
CO | HOLD/PERMIT | JAI/MONTE | PLUMB AND INSTALL FIXTURES | PER MONTE'S LIST
CO | HOLD | DANNY | INSTALL DOOR FRAME AND DOOR (DETERMINE WHICH WAY IT WILL OPEN)
NON-CO | NOW |  | MOVE SHELVING AND HARDWARE TO ROOM #3
NON-CO | HOLD | JAI/MONTE | REMOVE ANY PIPE NOT USED?
RESTROOMS - WOMENS |  |  |  | RESTROOMS - WOMENS
CATEGORY | STATUS | VOLUNTEER
CO | HOLD/PERMIT | JAI/MONTE | PLUMB AND INSTALL FIXTURES
NON-CO | NOW |  | CLEAN/PAINT OR REPLACE DOOR VENT | NEED SIZE
NON-CO | NOW |  | REMOVE PAPER TOWEL HOLDERS/INSTALL NEW | PATRICK - WHICH ARE WE USING?
NON-CO | NOW |  | SCRAPE/CLEAN UP VENT WINDOW. GET READY TO PAINT
RESTROOMS - MENS |  |  |  | RESTROOMS - MENS
CATEGORY | STATUS | VOLUNTEER
CO | HOLD/PERMIT | JAI/MONTE | PLUMB AND INSTALL FIXTURES
NON-CO | NOW |  | CLEAN/PAINT OR REPLACE DOOR VENT | NEED SIZE
NON-CO | NOW |  | REMOVE PAPER TOWEL HOLDERS/INSTALL NEW | PATRICK - WHICH ARE WE USING?
NON-CO | NOW |  | SCRAPE/CLEAN UP VENT WINDOW. GET READY TO PAINT
NON-CO | NOW |  | REMOVE DIVIDERS NOT USED AND STORE WITH OTHER DEMO MATERIALS
NON-CO | NOW |  | CLEAN AND PREP WALLS FOR PAINT, REMOVING ALL GLUE, EXCESS HARDWARE, CRACKS ECT.
NON-CO | HOLD |  | WHAT NEEDS TO HAPPEN WITH THE PIPE BY THE DOOR?
BOARD OFFICE |  |  |  | BOARD OFFICE
CATEGORY | STATUS | VOLUNTEER | TASK | SUPPLIES
NON-CO | NOW |  | FIX ROTTED DOOR TRIM
BREAK ROOM |  |  |  | BREAK ROOM
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | NOW |  | TIDY KITCHEN. WASH DISHES AND PUT AWAY. REMOVE UN-NECESSARY DISHES ON COUNTER TO AUCTION. IE CARAFES, CAKE CARRIER AND ETC
NON-CO | NOW |  | INSTALL WATER COOLER
NON-CO | NOW |  | CLEAN FLOOR - MOUSE DROPPINGS,
NON-CO | NOW |  | FIX LOOSE TILES
NON-CO | NOW |  | CLEAN VENT IN DOOR
NON-CO | NOW |  | CHECK/CHANGE IF NEEDED FURNACE FILTER
NON-CO | NOW |  | FIND TRASH CAN
NON-CO | NOW |  | FIND HOME FOR COMPUTER
NON-CO | NOW |  | HANG SMOKING SIGN - ASK DAVID WHERE
JANITOR CLOSETS |  |  |  | BREAK ROOM
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | NOW | BRAD TULL | ORGANIZE, LABEL, MAP AND POST MAP OF ALL THREE JANITOR CLOSETS
NON-CO | NOW | BRAD TULL | MAKE LIST OF NEEDED SUPPLIES
NON-CO | NOW | BRAD TULL | DISCARD/AUCTION EXCESS EQUIPMENT AND SUPPLIES
ROOM #1 CLASSROOM |  |  |  | ROOM #1 CLASSROOM
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | HOLD |  | ROOM FILLED WITH AUCTION ITEMS. SELL/ CLEAR ROOM! FURNITURE FLAGGED TO KEEP, DECIDE WHERE THEY GO.
ROOM #2 CLASSROOM |  |  |  | ROOM #2 CLASSROOM
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | ASAP |  | ROOM IS FULL OF FURNITURE - SELL. CLEAR ROOM
NON-CO | NOW |  | PULL OUT 2 BLUE CHAIRS. CAN THEY BE CLEANED UP AND ALL HARDWARE TIGHTENED TO MAKE CHAIRS USEABLE? RESTAIN/REFINISH WOOD. USE IN SEATING AREA IN FRONT HALLWAY
NON-CO | NOW |  | FIND GOOD STURDY SMALL CONVERSATION TABLE, REFINISH AND PUT ARTSY TOP ON IT. USE IN SEATING AREA IN FRONT HALLWAY.
ROOM #3 YOUTH/ADULT CLASSROOM |  |  |  | ROOM #3 YOUTH/ADULT CLASSROOM
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | NOW |  | REMOVE JACKS FROM UNDER WINDOW SHELVES
NON-CO | NOW |  | REMOVE COAT HOOKS FROM CLOSET. PUT IN AUCTION ROOM #4
NON-CO | NOW |  | BUILD SHELVING IN CLOSET AREA (PER LADEANA'S SPECIFICATIONS) POSSIBLY USE ADJUSTABLE SHELVING FROM PANTRY.
NON-CO | NOW |  | REMOVE BULLETIN BOARDS. SAVE TRIM. USE TO TRIM OUT WHITE BOARD | 4X8 WHITE BOARD
NON-CO | NOW |  | REPLACE PLYWOOD LEDGER BOARD AGAINST WINDOW. REMOVE GRATES AND REPLACE WITH WOOD SHELF? | NEED SUPPLY LIST. FIND REUSABLE SUPPLIES FROM DEMO?
NON-CO | NOW |  | FILL IN SHELVES WITH EXTRA BOARDS FROM OTHER UNITS. WIPE DOWN ALL SHELVING
NON-CO | NOW |  | WALL PAINT PREP. CLEAN ANY BRACKETS, GLUE/TAPE FROM WALLS. FILL HOLES, FIX CRACKS IN WALLS, COVER ELEC BOXES | NEED SUPPLY LIST. FIND REUSABLE SUPPLIES FROM DEMO?
NON-CO | HOLD |  | TAPE AND PAINT | NEED SUPPLY LIST, PAINT QUANITY
NON-CO | NOW |  | SCRAPE LOOSE PAINT FROM WINDOW FRAMES. PREP FOR PAINT
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | NOW |  | CLEAN, MOP AND BUFF FLOOR | NEED FLOOR BUFFER
NON-CO | NOW |  | REMOVE LOW CHILDREN'S TABLE
NON-CO | NOW |  | RAISE LOW ADJUSTABLE ROUND TABLE
NON-CO | NOW |  | NEED 2 BLUE LUNCH ROOM TABLES AND 2 BENCHES - ASK LADEANA IF SHE'D RATHER HAVE 4 BENCHES
NON-CO | NOW |  | PUT CASTERS UNDER RED CUBE CABINET | CASTERS, OTHER SUPPLIES?
NON-CO | NOW |  | DOUGLAS LOUNGE - PUT NEW WORK TOP ON CABINET AND CASTERS ON THE BOTTOM | CASTERS, OTHER SUPPLIES?
NON-CO | NOW |  | REMOVE WIRE HANGING FROM CEILING ACROSS ROOM
NON-CO | NOW |  | PUT TV IN AUCTION ROOM #4
ROOM #4 - LOUNGE |  |  |  | ROOM #4 - LOUNGE
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | NOW |  | MOVE TV FROM DOUGLAS - SET UP
NON-CO | NOW |  | WIPE DOWN SHELVING, FILL IN MISSING WITH EXTRA UN-USED
NON-CO | NOW |  | CLEAN FLOORS / BUFF
NON-CO | NOW |  | PREP FOR PAINT. REMOVE TAPE, GLUE, UN-NECESSARY HARDWARE, FILL HOLES, FIX AND CRACKS
NON-CO | NOW |  | REMOVE GRATES AND FILL IN SPACE WITH WOOD SHELVING
| HOLD |  | FIND NEW HOME FOR LUNCH ROOM TABLES
NON-CO | NOW | KIP | RECOVER, UPDATE POOL TABLE
ROOM #7 - ERP |  |  |  | ROOM #7 - ERP
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
NON-CO | ASAP |  | CLEAN FLOOR, REPLACE MISSING TILE AND PAINT EPOXY
NON-CO | NOW |  | FIX DOOR OR REPLACE
NON-CO | NOW |  | PUT TEXTILE MATERIAL IN TEXTILE ROOM
NON-CO | QUESTION |  | KEEPING WINDOW SHELVING?
NON-CO | QUESTION |  | KEEPING BULLETIN BOARDS?
NON-CO | NOW |  | SCRAPE WINDOW FRAMES, PREP FOR PAINT
NON-CO | NOW |  | PREP FOR PAINT: REMOVE TAPE, GLUE, UN-NECESSARY HARDWARE, FILL HOLES, FIX CRACKS
NON-CO | NOW |  | REPLACE PLYWOOD WINDOW LEDGE BOARD
NON-CO | NOW |  | CLEAN WINDOWS
ROOM #8 - TEXTILE |  |  |  | ROOM #8 - TEXTILE
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
NON-CO | ASAP |  | CLEAN FLOOR, REPLACE MISSING TILE AND PAINT EPOXY
NON-CO | NOW |  | FIX DOOR OR REPLACE
NON-CO | QUESTION |  | KEEPING WINDOW SHELVING?
NON-CO | QUESTION |  | KEEPING BULLETIN BOARDS?
NON-CO | NOW |  | SCRAPE WINDOW FRAMES, PREP FOR PAINT
NON-CO | NOW |  | PREP FOR PAINT: REMOVE TAPE, GLUE, UN-NECESSARY HARDWARE, FILL HOLES, FIX CRACKS
NON-CO | NOW |  | REPLACE PLYWOOD WINDOW LEDGE BOARD
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | NOW |  | KEEPING PULL DOWN SCREEN?
NON-CO | NOW |  | RELOCATE PING-PONG TABLE
NON-CO | NOW |  | CARRY OUT TRASH
NON-CO | NOW |  | WHERE WE USE THE SHEET ROCK, INSULATION AND OTHER BUILDING SUPPLIES
ROOM #10 - FAB LAB |  |  |  | ROOM #10 - FAB LAB
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
NON-CO | ASAP |  | CLEAN FLOOR, REPLACE MISSING TILE AND PAINT EPOXY
NON-CO | NOW |  | FIX DOOR OR REPLACE
NON-CO | QUESTION |  | KEEPING WINDOW SHELVING?
NON-CO | QUESTION |  | KEEPING BULLETIN BOARDS?
NON-CO | NOW |  | SCRAPE WINDOW FRAMES, PREP FOR PAINT
NON-CO | NOW |  | PREP FOR PAINT: REMOVE TAPE, GLUE, UN-NECESSARY HARDWARE, CORK, FILL HOLES, FIX CRACKS
NON-CO | NOW |  | REPLACE PLYWOOD WINDOW LEDGE BOARD
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | NOW |  | MOVE MIRROR, PAPER TOWEL HOLDER, I BEAMS, GLASS, BRICKS AND CONCRETE
ROOM #11 - WOODSHOP 1 |  |  |  | ROOM #11 - WOODSHOP 1
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
CO | ASAP |  | FIRE DOORS
CO | ASAP |  | FRAME FIRE WALLS, INSPECTION, DRYWALL, MUD AND TAPE
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
NON-CO | ASAP |  | CLEAN FLOOR, REPLACE MISSING TILE AND PAINT EPOXY
NON-CO | NOW |  | FIX DOOR OR REPLACE
NON-CO | QUESTION |  | KEEPING WINDOW SHELVING?
NON-CO | QUESTION |  | KEEPING BULLETIN BOARDS?
NON-CO | NOW |  | SCRAPE WINDOW FRAMES, PREP FOR PAINT
NON-CO | NOW |  | PREP FOR PAINT: REMOVE TAPE, GLUE, UN-NECESSARY HARDWARE, CORK, FILL HOLES, FIX CRACKS
NON-CO | NOW |  | REPLACE PLYWOOD WINDOW LEDGE BOARD
NON-CO | NOW |  | CLEAN WINDOWS
ROOM #12 - WOODSHOP 2 |  |  |  | ROOM #12 - WOODSHOP 2
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
CO | ASAP |  | FIRE DOORS
CO | ASAP |  | FRAME FIRE WALLS, INSPECTION, DRYWALL, MUD AND TAPE
NON-CO | ASAP |  | REMOVE BRICK DEBRIS
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
NON-CO | ASAP |  | CLEAN FLOOR, REPLACE MISSING TILE AND PAINT EPOXY
NON-CO | NOW |  | FIX DOOR OR REPLACE
NON-CO | QUESTION |  | KEEPING WINDOW SHELVING?
NON-CO | QUESTION |  | KEEPING BULLETIN BOARDS?
NON-CO | NOW |  | SCRAPE WINDOW FRAMES, PREP FOR PAINT
NON-CO | NOW |  | PREP FOR PAINT: REMOVE TAPE, GLUE, UN-NECESSARY HARDWARE, CORK, FILL HOLES, FIX CRACKS
NON-CO | NOW |  | REPLACE PLYWOOD WINDOW LEDGE BOARD
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | NOW |  | RELOCATE STAGE, BLUE TABLES
ROOM #13 METAL SHOP 1 |  |  |  | ROOM #13 METAL SHOP 1
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
CO | ASAP |  | FIRE DOORS
CO | ASAP |  | FRAME FIRE WALLS, INSPECTION, DRYWALL, MUD AND TAPE
NON-CO | ASAP |  | REMOVE BRICK DEBRIS
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
NON-CO | ASAP |  | CLEAN FLOOR, REPLACE MISSING TILE AND PAINT EPOXY
NON-CO | NOW |  | FIX DOOR OR REPLACE
NON-CO | QUESTION |  | KEEPING WINDOW SHELVING?
NON-CO | QUESTION |  | KEEPING BULLETIN BOARDS?
NON-CO | NOW |  | SCRAPE WINDOW FRAMES, PREP FOR PAINT
NON-CO | NOW |  | PREP FOR PAINT: REMOVE TAPE, GLUE, UN-NECESSARY HARDWARE, CORK, FILL HOLES, FIX CRACKS
NON-CO | NOW |  | REPLACE PLYWOOD WINDOW LEDGE BOARD
NON-CO | NOW |  | CLEAN WINDOWS
ROOM 14 - METAL SHOP 2 |  |  |  | ROOM 14 - METAL SHOP 2
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
CO | ASAP |  | FIRE DOORS
CO | ASAP |  | FRAME FIRE WALLS, INSPECTION, DRYWALL, MUD AND TAPE
NON-CO | ASAP |  | REMOVE BRICK DEBRIS
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
NON-CO | ASAP |  | CLEAN FLOOR, REPLACE MISSING TILE AND PAINT EPOXY
NON-CO | NOW |  | FIX DOOR OR REPLACE
NON-CO | QUESTION |  | KEEPING WINDOW SHELVING?
NON-CO | QUESTION |  | KEEPING BULLETIN BOARDS?
NON-CO | NOW |  | SCRAPE WINDOW FRAMES, PREP FOR PAINT
NON-CO | NOW |  | PREP FOR PAINT: REMOVE TAPE, GLUE, UN-NECESSARY HARDWARE, CORK, FILL HOLES, FIX CRACKS
NON-CO | NOW |  | REPLACE PLYWOOD WINDOW LEDGE BOARD
NON-CO | NOW |  | CLEAN WINDOWS
NON-CO | HOLD |  | CLEAR ROOM OF EXTRA STUFF
ROOM - CERAMICS ROOM |  |  |  | ROOM - CERAMICS ROOM
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
ROOM - CERAMICS KILN |  |  |  | ROOM - CERAMICS ROOM
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT
NON-CO | ASAP |  | INSTALL PLUMBING
NON-CO | ASAP |  | FIX FLOOR
NON-CO | ASAP |  | EPOXY WALLS FOR WATER REQUIREMENTS
NON-CO | ASAP |  | CAP OFF TOILETS
ROOM - TEXTILE WET STUDIO |  |  |  | ROOM - TEXTILE WET STUDIO
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
NON-CO | ASAP |  | PULL ELECTRICITY FOR EQUIPMENT (PULL FOR DRYER TOO)
NON-CO | ASAP |  | INSTALL PLUMBING ([PLUMB FOR WASHER )
NON-CO | ASAP |  | FIX FLOOR
NON-CO | ASAP |  | EPOXY WALLS FOR WATER REQUIREMENTS
NON-CO | ASAP |  | CAP OFF TOILETS
OUTDOOR
CATEGORY | STATUS | VOLUNTEER |  | SUPPLIES
CO | ASAP |  | FIX ADA PARKING PAD AND ENTRY TO BUILDING
CO | IN PROGRESS | PAULA | PARKING AREA
CO | PERMIT |  | DUMPSTER SCREEN
NON-CO | NOW |  | FIX GRADE MAKING SWELL IN COURT YARD AREA